## create an excel sheet with the
Sprint | Task ID | User Story ID | Task Description | Assignee | Priority | Estimated MD | Remaining MD | Status | Notes
S1 | T1 | US1 | Setup development environment (STM32CubeIDE / Arduino) | Name1 | High | 0.5 | 0.5 | Done | Initial setup
S1 | T2 | US2 | Interface MPU6050 with microcontroller using I2C | Name1 | High | 1 | 1 | To Do | Sensor connection
S1 | T3 | US2 | Read accelerometer data | Name1 | High | 2 | 2 | To Do | Vibration detection
S1 | T4 | US2 | Read gyroscope data | Name1 | High | 2 | 2 | To Do | Tilt detection
S1 | T5 | US3 | Display sensor data via UART for debugging | Name1 | High | 0.5 | 0.5 | To Do | Verification
S2 | T6 | US4 | Configure MPU6050 interrupt | Name1 | High | 1.5 | 1.5 | To Do | Key feature
S2 | T7 | US5 | Implement threshold-based vibration detection | Name1 | High | 2 | 2 | To Do | Core logic
S2 | T8 | US5 | Implement tilt detection logic using gyroscope | Name1 | High | 2 | 2 | To Do | Condition check
S2 | T9 | US5 | Classify system status (NORMAL / HIGH_VIBRATION / TILT_ERROR) | Name1 | High | 2 | 2 | To Do | Decision logic
S3 | T10 | US6 | Interface LoRa SX1278 with microcontroller (SPI) | Name1 | High | 1.5 | 1.5 | To Do | Communication setup
S3 | T11 | US6 | Send data via LoRa transmitter | Name1 | High | 2 | 2 | To Do | TX node
S3 | T12 | US6 | Add node ID to transmitted data | Name1 | Medium | 2 | 2 | To Do | Identification
S4 | T13 | US7 | Setup LoRa receiver node | Name1 | High | 1.5 | 1.5 | To Do | Gateway
S4 | T14 | US7 | Receive and decode LoRa data | Name1 | High | 2 | 2 | To Do | Data handling
S4 | T15 | US7 | Display output (OK / WARNING / DANGER) | Name1 | High | 2 | 2 | To Do | Output display
S5 | T16 | US8 | Perform system integration (sensor + LoRa + logic) | Name1 | High | 2 | 2 | To Do | Combine modules
S5 | T17 | US9 | Debug system using UART logs | Name1 | Medium | 2 | 2 | To Do | Troubleshooting
S5 | T18 | US10 | Test system with vibration and tilt conditions | Name1 | High | 2 | 2 | To Do | Validation
S5 | T19 | US11 | Optimize power using interrupt-based operation | Name1 | Medium | 2 | 2 | To Do | Efficiency
S6 | T20 | US12 | Finalize system and prepare demonstration | Name1 | High | 1 | 1 | To Do
Abbreviations
| PS | Platform Setup
| DRV | Driver and RTOS integration
| APP | Application
| QA | Quality Assurance